## COCOMO II Calculations
COCOMO II - EFFORT AND DURATION CALCULATION
1. FUNCTION POINTS
Parameter | Value | Formula
UFP (Unadjusted Function Points) | 81
VAF (Value Adjustment Factor) | 1.09
FP (Adjusted Function Points) | 88.29 | UFP × VAF
2. FP → SLOC CONVERSION
Language | % Project | FP Allocated | SLOC/FP | SLOC
HTML/CSS | 55 | 48.56 | 15 | 728
JavaScript | 15 | 13.24 | 47 | 622
Dockerfile | 15 | 13.24 | 15 | 199
PHP | 15 | 13.24 | 64 | 847
|  |  | TOTAL SLOC: | 2396
|  |  | KSLOC: | 2.4
3. SCALE FACTORS
Factor | Rating | Value | Description
PREC (Precedentedness) | Nominal | 3.72 | Experience in similar projects
FLEX (Development Flexibility) | High | 2.03 | Requirements flexibility
RESL (Risk Resolution) | Nominal | 4.24 | Risk management
TEAM (Team Cohesion) | High | 2.19 | Team cohesion
PMAT (Process Maturity) | Nominal | 4.68 | Process maturity
Sum of Scale Factors (Σ SF) |  | 16.86
Exponent B |  | 0.91 | (constant)
Exponent E |  | 1.0786 | B + 0.01 × Σ(SF)
4. EFFORT MULTIPLIERS
Category | Factor | Value | Notes
PRODUCT | RELY (Required Reliability) | 0.92 | Required reliability
| DATA (Database Size) | 0.9 | Database size
| CPLX (Product Complexity) | 1 | Product complexity
| RUSE (Reuse Required) | 1 | Required reusability
| DOCU (Documentation) | 1 | Documentation needs
PLATFORM | TIME (Execution Time) | 1 | Execution time constraints
| STOR (Main Storage) | 1 | Memory constraints
| PVOL (Platform Volatility) | 1 | Platform volatility
PERSONNEL | ACAP (Analyst Capability) | 1 | Analyst capability
| PCAP (Programmer Capability) | 1 | Programmer capability
| PCON (Personnel Continuity) | 1 | Personnel continuity
| APEX (Applications Experience) | 1 | Applications experience
| PLEX (Platform Experience) | 1 | Platform experience
| LTEX (Language & Tools Exp) | 1 | Language/tools experience
PROJECT | TOOL (Use of Tools) | 1 | Use of CASE tools
| SITE (Multisite Development) | 1 | Multisite development
| SCED (Schedule Constraint) | 1 | Schedule constraints
Product of Effort Multipliers (∏ EM) |  | 0.83
5. EFFORT CALCULATION (Person-Months)
Parameter | Value | Formula
Constant A | 2.94 | (calibration constant)
KSLOC | 2.4 | (from section 2)
Exponent E | 1.0786 | (from section 3)
Product EM | 0.83 | (from section 4)
EFFORT (PM) | 6.37 | A × Size^E × ∏EM
6. DURATION CALCULATION (Months)
Parameter | Value | Formula
Constant D | 0.28 | (base constant)
Exponent B | 0.91 | (from section 3)
Exponent E | 1.0786 | (from section 3)
Exponent F | 0.3137 | D + 0.2 × (E - B)
Base constant | 3.67 | (constant)
Effort (PM) | 6.37 | (from section 5)
DURATION (months) | 6.38 | 3.67 × Effort^F
7. AVERAGE STAFF
Parameter | Value | Formula
Effort (PM) | 6.37 | (from section 5)
Duration (months) | 6.38 | (from section 6)
AVERAGE STAFF | 1 | Effort / Duration
8. INTERPRETATION FOR TEAM OF 3 PEOPLE
Metric | Value | Unit
Months per person | 2.12 | months
Working days per person | 42 | days
Estimated hours per person (8h/day) | 339 | hours

## Reference Tables
COCOMO II REFERENCE TABLES
SCALE FACTORS - REFERENCE VALUES
PREC - Precedentedness (Experience in similar projects)
Rating | Value | Description
Very Low | 6.2 | Never done similar projects
Low | 4.96 | Little similar experience
Nominal | 3.72 | Average experience
High | 2.48 | Good similar experience
Very High | 1.24 | Extensive similar experience
Extra High | 0 | Domain experts
FLEX - Development Flexibility (Requirements flexibility)
Rating | Value | Description
Very Low | 5.07 | Very rigid requirements
Low | 4.05 | Few variations possible
Nominal | 3.04 | Average flexibility
High | 2.03 | Flexible requirements
Very High | 1.01 | Maximum flexibility
Extra High | 0 | Total flexibility
RESL - Risk Resolution (Risk management)
Rating | Value | Description
Very Low | 7.07 | No risk management
Low | 5.65 | Minimal risk management
Nominal | 4.24 | Basic risk management
High | 2.83 | Good risk management
Very High | 1.41 | Complete risk management
Extra High | 0 | Optimal risk management
TEAM - Team Cohesion (Team cohesion)
Rating | Value | Description
Very Low | 5.48 | Team in conflict/dispersed
Low | 4.38 | Limited collaboration
Nominal | 3.29 | Normal collaboration
High | 2.19 | Good collaboration
Very High | 1.1 | Perfectly cohesive team
Extra High | 0 | Optimal team
PMAT - Process Maturity (Process maturity)
Rating | Value | Description
Very Low | 7.8 | No defined processes
Low | 6.24 | Minimal processes
Nominal | 4.68 | Basic processes (CMMI level 1-2)
High | 3.12 | Defined processes (CMMI level 3)
Very High | 1.56 | Mature processes (CMMI level 4-5)
Extra High | 0 | Optimal processes
EFFORT MULTIPLIERS - TYPICAL VALUES
Rating | Very Low | Low | Nominal | High | Very High | Extra High
Typical value | 0.73 | 0.87 | 1 | 1.15 | 1.3 | 1.65
| (reduces effort) | (reduces effort) | (neutral) | (increases effort) | (increases effort) | (increases effort)
Notes:
- Values < 1.00 reduce required effort
- Values > 1.00 increase required effort
- Value 1.00 = nominal/average situation
LANGUAGE CONVERSION FACTORS → SLOC/FP
Language | SLOC per Function Point
JavaScript | 47
PHP | 64
HTML/CSS | 15
Dockerfile | 15